## BOM Additions
BOM Post-Release Addition Tracker | [19 empty] | Procurement Use
# | Job No. | Job Description | BOM Release Date | Addition Date | Days After Release | Part No. | Part Description | Qty | Unit Cost (AUD) | Total Cost (AUD) | Reason Code | Requested By | Approved By | Procurement Status | Supplier | PO Number | Required By | Expected Delivery | Actual Delivery | Delivery Status | Notes
| 801254 | Aviation Refueller Mk4 | 2026-07-28 | 2026-08-05 |  | HYD-SEAL-088 | Hydraulic seal kit — actuator arm | 2 | 145 |  | Engineering Change | T. Wallace | G. Kalms | Ordered | Hydraforce Pty Ltd | PO-2026-0412 | 2026-08-20 | 2026-08-18 |  |  | Required before cab assembly — flagged by engineering 4/8
| 801235 |  |  |  |  | 10000-10-12 |  | 1 | 23.89 |  |  |  |  | Complete | FROM STOCK
| 801236 |  |  |  |  | 10000-10-12 |  | 1 | 23.89 |  |  |  |  | Complete | FROM STOCK
| 801235 |  |  |  |  | 10000-10-35 |  | 2 | 99.24 |  |  |  |  | Complete | FROM STOCK
| 801236 |  |  |  |  | 10000-10-35 |  | 2 | 99.24 |  |  |  |  | Complete | FROM STOCK
| 801235 |  |  |  |  | 10000-10-37 |  | 1 | 24 |  |  |  |  | Complete | FROM STOCK
| 801236 |  |  |  |  | 10000-10-37 |  | 1 | 24 |  |  |  |  | Complete | FROM STOCK
| 801235 |  |  |  |  | 10000-10-67 |  | 1 | 4.84 |  |  |  |  | Complete | FROM STOCK
| 801236 |  |  |  |  | 10000-10-67 |  | 1 | 4.84 |  |  |  |  | Complete | FROM STOCK
| 801216 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801217 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801218 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801219 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801237 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801238 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801239 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801240 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 25699-FLOW | FLOW LABEL | 1 | 71.5 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 3000-03-05 | DEADMAN HANDLE TRAY LARGE | 1 | 118.72 |  |  |  |  | Ordered | HUNT | PO119947
| 801241 |  |  |  |  | 3000-32-161 | BRACKET VALVE OPERATION LABEL FLAT 4" MANNTEK | 1 | 6.8 |  |  |  |  | Ordered | HUNT | PO119948
| 801241 |  |  |  |  | 3000-32-55 | VALVE OPERATION LABEL BRACKET | 3 | 14.95 |  |  |  |  | Ordered | HUNT | PO119949
| 801216 |  |  |  |  | 4600-06-18 | OPW295 OVERWING NOZZLE INTERLOCK BRACKET | 1 | 148.64 |  |  |  |  | Ordered | HUNT | PO119947
| 801217 |  |  |  |  | 4600-06-18 | OPW295 OVERWING NOZZLE INTERLOCK BRACKET | 1 | 148.64 |  |  |  |  | Ordered | HUNT | PO119948
| 801218 |  |  |  |  | 4600-06-18 | OPW295 OVERWING NOZZLE INTERLOCK BRACKET | 1 | 148.64 |  |  |  |  | Ordered | HUNT | PO119949
| 801219 |  |  |  |  | 4600-06-18 | OPW295 OVERWING NOZZLE INTERLOCK BRACKET | 1 | 148.64 |  |  |  |  | Ordered | HUNT | PO119950
| 801237 |  |  |  |  | 4600-06-18 | OPW295 OVERWING NOZZLE INTERLOCK BRACKET | 1 | 148.64 |  |  |  |  | Ordered | HUNT | PO119951
| 801238 |  |  |  |  | 4600-06-18 | OPW295 OVERWING NOZZLE INTERLOCK BRACKET | 1 | 148.64 |  |  |  |  | Ordered | HUNT | PO119952
| 801239 |  |  |  |  | 4600-06-18 | OPW295 OVERWING NOZZLE INTERLOCK BRACKET | 1 | 148.64 |  |  |  |  | Ordered | HUNT | PO119953
| 801240 |  |  |  |  | 4600-06-18 | OPW295 OVERWING NOZZLE INTERLOCK BRACKET | 1 | 148.64 |  |  |  |  | Ordered | HUNT | PO119954
| 801235 |  |  |  |  | 50700100086 | GASKET ISO 7707 4 HOLE DIAM80 10000-10-103 | 1 | 2.1 |  |  |  |  | Ordered | OMFB | PO120110
| 801236 |  |  |  |  | 50700100086 | GASKET ISO 7707 4 HOLE DIAM80 10000-10-103 | 1 | 2.1 |  |  |  |  | Ordered | OMFB | PO120110
| 801267 |  |  |  |  | 6000-08-63 | LOGO PANEL : SWIVEL REEL LADDER STOWAGE | 1 | 172.86 |  |  |  |  | Ordered | HUNT | PO120112
| 801269 |  |  |  |  | 6020-02-19 | DOUBLE SHEAR LINK PLT-ZP BLUE | 1 | 24.9 |  |  | saurabh |  | Ordered | HUNT | PO120254
| 801270 |  |  |  |  | 6020-02-19 | DOUBLE SHEAR LINK PLT-ZP BLUE | 1 | 24.9 |  |  |  |  | Ordered | HUNT | PO120255
| 801235 |  |  |  |  | 7000-06-138 | CONTROL PANEL LABEL | 1 | 275 |  |  |  |  | Ordered | EMTAN | PO119240
| 801236 |  |  |  |  | 7000-06-138 | CONTROL PANEL LABEL | 1 | 275 |  |  |  |  | Ordered | EMTAN | PO119240
| 801281 |  |  |  |  | 7000-29-07 | BRACKET DB MOUNT TO CONTROL PANEL | 1 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801281 |  |  |  |  | 7000-29-08 | BRACKET SIGN PANEL DB COVER | 1 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801281 |  |  |  |  | 7000-29-09 | BRACKET DB MOUNT | 1 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801241 |  |  |  |  | 7000-30-238 | BRACKET - BALL VALVE LABEL FLAT SUIT 3" MANNTEK | 1 | 10.57 |  |  |  |  | Ordered | HUNT | PO119950
| 801216 |  |  |  |  | 7000-30-315 | NIPPLE TOE SS G316 BSPT 1/2" | 1 | 11.64 |  |  |  |  | Ordered | HUNT | PO119947
| 801217 |  |  |  |  | 7000-30-315 | BRACKET PRESSURE SWITCH COVER | 1 | 11.64 |  |  |  |  | Ordered | HUNT | PO119948
| 801218 |  |  |  |  | 7000-30-315 | BRACKET PRESSURE SWITCH COVER | 1 | 11.64 |  |  |  |  | Ordered | HUNT | PO119949
| 801219 |  |  |  |  | 7000-30-315 | BRACKET PRESSURE SWITCH COVER | 1 | 11.64 |  |  |  |  | Ordered | HUNT | PO119950
| 801237 |  |  |  |  | 7000-30-315 | BRACKET PRESSURE SWITCH COVER | 1 | 11.64 |  |  |  |  | Ordered | HUNT | PO119951
| 801238 |  |  |  |  | 7000-30-315 | BRACKET PRESSURE SWITCH COVER | 1 | 11.64 |  |  |  |  | Ordered | HUNT | PO119952
| 801239 |  |  |  |  | 7000-30-315 | BRACKET PRESSURE SWITCH COVER | 1 | 11.64 |  |  |  |  | Ordered | HUNT | PO119953
| 801240 |  |  |  |  | 7000-30-315 | BRACKET PRESSURE SWITCH COVER | 1 | 11.64 |  |  |  |  | Ordered | HUNT | PO119954
| 801281 |  |  |  |  | 7000-30-322 | BRACKET METER SUPPORT BM400 | 2 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801281 |  |  |  |  | 7000-30-325 | BRACKET BALL VALVE MOUNT 6" RH | 1 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801281 |  |  |  |  | 7000-30-326 | BRACKET BALL VALVE MOUNT 6" LH | 1 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801281 |  |  |  |  | 7000-30-327 | BRACKET ALJAC MOUNT | 1 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801281 |  |  |  |  | 7000-30-329 | BRACKET CONTROL PANEL MOUNT | 2 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801281 |  |  |  |  | 7000-30-330 | BRACKET BALL VALVE SUPPORT | 1 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801281 |  |  |  |  | 7000-41-24 | BRACKET PUMP MOUNT 06C1-DA | 1 |  |  |  | saurabh |  | Ordered | HUNT | PO12055
| 801241 |  |  |  |  | 9300-01-114 | Label - Air Tank Drain - ENGLISH ARABIC | 1 | 10 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-117 | STICKER - BATTERY ISOLATOR OFF/ON - ENGLISH ARABIC | 1 | 10 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-119 | STICKER - DRAIN AIR TANKS DAILY - ENGLISH ARABIC | 1 | 16 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-127 | STICKER COLLECTOR TANK INSPECTED CLEANED DATE ENGLISH ARABIC | 1 | 20 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-130 | LABEL - EMER. POWER STOP PUSH TO ACTIVATE - ENGLISH ARABIC | 1 | 10 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-132 | LABEL WARNING DO NOT USE AS A STEP ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-133 | LABEL - EMERGENCY STOP - ENGLISH ARABIC 80 x 35 | 2 | 10 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-134 | LABEL FILTER VESSEL SHOW FLOW - ENGLISH ARABIC | 1 | 10 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-135 | LABEL ALJAC SHOW FLOW - ENGLISH ARABIC | 1 | 10 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801241 |  |  |  |  | 9300-01-136 | LABEL - HYDRANT DISPENSER BALL VALVE OPEN/CLOSED - ENGLISH ARABIC | 1 | 10 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801216 |  |  |  |  | 9300-01-137 | LABEL THIS IS NOT A FILL POINT - ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801217 |  |  |  |  | 9300-01-137 | LABEL THIS IS NOT A FILL POINT - ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801218 |  |  |  |  | 9300-01-137 | LABEL THIS IS NOT A FILL POINT - ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801219 |  |  |  |  | 9300-01-137 | LABEL THIS IS NOT A FILL POINT - ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801237 |  |  |  |  | 9300-01-137 | LABEL THIS IS NOT A FILL POINT - ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801238 |  |  |  |  | 9300-01-137 | LABEL THIS IS NOT A FILL POINT - ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801239 |  |  |  |  | 9300-01-137 | LABEL THIS IS NOT A FILL POINT - ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801240 |  |  |  |  | 9300-01-137 | LABEL THIS IS NOT A FILL POINT - ENGLISH ARABIC | 1 | 80 |  |  | Sri |  | Ordered | Niddrie | PO119955
| 801217 |  |  |  |  | BSPCRN025X020A | HEXAGON REDUCING NIPPLE R25XR20 CL3000 BSP 316 | 4 | 31 |  |  |  |  | Ordered | PROCHEM | PO120094
| 801218 |  |  |  |  | BSPCRN025X020A | HEXAGON REDUCING NIPPLE R25XR20 CL3000 BSP 317 | 4 | 31 |  |  |  |  | Ordered | PROCHEM | PO120094
| 801219 |  |  |  |  | BSPCRN025X020A | HEXAGON REDUCING NIPPLE R25XR20 CL3000 BSP 318 | 4 | 31 |  |  |  |  | Ordered | PROCHEM | PO120094
| 801237 |  |  |  |  | BSPCRN025X020A | HEXAGON REDUCING NIPPLE R25XR20 CL3000 BSP 319 | 4 | 31 |  |  |  |  | Ordered | PROCHEM | PO120094
| 801238 |  |  |  |  | BSPCRN025X020A | HEXAGON REDUCING NIPPLE R25XR20 CL3000 BSP 320 | 4 | 31 |  |  |  |  | Ordered | PROCHEM | PO120094
| 801239 |  |  |  |  | BSPCRN025X020A | HEXAGON REDUCING NIPPLE R25XR20 CL3000 BSP 321 | 4 | 31 |  |  |  |  | Ordered | PROCHEM | PO120094
| 801240 |  |  |  |  | BSPCRN025X020A | HEXAGON REDUCING NIPPLE R25XR20 CL3000 BSP 322 | 4 | 31 |  |  |  |  | Ordered | PROCHEM | PO120094
| 801216 |  |  |  |  | CLY33 | CHECKLINK 33MM YELLOW | 60 | 2.35 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801217 |  |  |  |  | CLY33 | CHECKLINK 33MM YELLOW | 60 | 2.35 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801218 |  |  |  |  | CLY33 | CHECKLINK 33MM YELLOW | 60 | 2.35 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801219 |  |  |  |  | CLY33 | CHECKLINK 33MM YELLOW | 60 | 2.35 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801237 |  |  |  |  | CLY33 | CHECKLINK 33MM YELLOW | 60 | 2.35 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801238 |  |  |  |  | CLY33 | CHECKLINK 33MM YELLOW | 60 | 2.35 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801239 |  |  |  |  | CLY33 | CHECKLINK 33MM YELLOW | 60 | 2.35 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801240 |  |  |  |  | CLY33 | CHECKLINK 33MM YELLOW | 60 | 2.35 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801216 |  |  |  |  | CP34Y | WHEEL LOCK INDICATOR 34MM | 40 | 0.95 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801217 |  |  |  |  | CP34Y | WHEEL LOCK INDICATOR 34MM | 40 | 0.95 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801218 |  |  |  |  | CP34Y | WHEEL LOCK INDICATOR 34MM | 40 | 0.95 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801219 |  |  |  |  | CP34Y | WHEEL LOCK INDICATOR 34MM | 40 | 0.95 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801237 |  |  |  |  | CP34Y | WHEEL LOCK INDICATOR 34MM | 40 | 0.95 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801238 |  |  |  |  | CP34Y | WHEEL LOCK INDICATOR 34MM | 40 | 0.95 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801239 |  |  |  |  | CP34Y | WHEEL LOCK INDICATOR 34MM | 40 | 0.95 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801240 |  |  |  |  | CP34Y | WHEEL LOCK INDICATOR 34MM | 40 | 0.95 |  |  |  |  | Ordered | CP SAFETY | PO119949
| 801252 |  |  |  |  | G7580 8 | Technopolymer Fitting Tube To Tube Connector 8mm Tube | 2 | 2.71 |  |  | Sri |  | Ordered | Net Automation | PO120150
| 801253 |  |  |  |  | G7580 8 | Technopolymer Fitting Tube To Tube Connector 8mm Tube | 2 | 2.71 |  |  | Sri |  | Ordered | Net Automation | PO120150
| 801254 |  |  |  |  | G7580 8 | Technopolymer Fitting Tube To Tube Connector 8mm Tube | 2 | 2.71 |  |  | Sri |  | Ordered | Net Automation | PO120150
| 801255 |  |  |  |  | G7580 8 | Technopolymer Fitting Tube To Tube Connector 8mm Tube | 2 | 2.71 |  |  | Sri |  | Ordered | Net Automation | PO120150
| 801257 |  |  |  |  | G7580 8 | Technopolymer Fitting Tube To Tube Connector 8mm Tube | 2 | 2.71 |  |  | Sri |  | Ordered | Net Automation | PO120150
| 801258 |  |  |  |  | G7580 8 | Technopolymer Fitting Tube To Tube Connector 8mm Tube | 2 | 2.71 |  |  | Sri |  | Ordered | Net Automation | PO120150
| 801259 |  |  |  |  | G7580 8 | Technopolymer Fitting Tube To Tube Connector 8mm Tube | 2 | 2.71 |  |  | Sri |  | Ordered | Net Automation | PO120150
| 801260 |  |  |  |  | G7580 8 | Technopolymer Fitting Tube To Tube Connector 8mm Tube | 2 | 2.71 |  |  | Sri |  | Ordered | Net Automation | PO120150
| 801216 |  |  |  |  | NA-IND-30715G | 22MM RG INDICATOR REPL PXV | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801217 |  |  |  |  | NA-IND-30715G | 22MM RG INDICATOR REPL PXV | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801218 |  |  |  |  | NA-IND-30715G | 22MM RG INDICATOR REPL PXV | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801219 |  |  |  |  | NA-IND-30715G | 22MM RG INDICATOR REPL PXV | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801237 |  |  |  |  | NA-IND-30715G | 22MM RG INDICATOR REPL PXV | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801238 |  |  |  |  | NA-IND-30715G | 22MM RG INDICATOR REPL PXV | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801239 |  |  |  |  | NA-IND-30715G | 22MM RG INDICATOR REPL PXV | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801240 |  |  |  |  | NA-IND-30715G | 22MM RG INDICATOR REPL PXV | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801215 |  |  |  |  | PS7-4 | LADDER | 1 | 140 |  |  |  |  | Ordered | Net Automation | PO119961
| 801216 |  |  |  |  | SKGPMT | SPILL KIT 25L | 1 | 85.13 |  |  |  |  | Ordered | GLOBAL SPILL CONTROL | PO117056
| 801217 |  |  |  |  | SKGPMT | SPILL KIT 25L | 1 | 85.13 |  |  |  |  | Ordered | GLOBAL SPILL CONTROL | PO117056
| 801218 |  |  |  |  | SKGPMT | SPILL KIT 25L | 1 | 85.13 |  |  |  |  | Ordered | GLOBAL SPILL CONTROL | PO117056
| 801219 |  |  |  |  | SKGPMT | SPILL KIT 25L | 1 | 85.13 |  |  |  |  | Ordered | GLOBAL SPILL CONTROL | PO117056
| 801237 |  |  |  |  | SKGPMT | SPILL KIT 25L | 1 | 85.13 |  |  |  |  | Ordered | GLOBAL SPILL CONTROL | PO117056
| 801238 |  |  |  |  | SKGPMT | SPILL KIT 25L | 1 | 85.13 |  |  |  |  | Ordered | GLOBAL SPILL CONTROL | PO117056
| 801239 |  |  |  |  | SKGPMT | SPILL KIT 25L | 1 | 85.13 |  |  |  |  | Ordered | GLOBAL SPILL CONTROL | PO117056
| 801240 |  |  |  |  | SKGPMT | SPILL KIT 25L | 1 | 85.13 |  |  |  |  | Ordered | GLOBAL SPILL CONTROL | PO117056
HOW TO USE: Row 3 is an example (yellow). Data rows 4–123 populated from first import batch. Columns F, K, U are calculated — do not edit. Amber cost = >$500. See Job Summary tab for per-job totals. Add BOM Release Date (col D) and Addition Date (col E) when known.
Formulas:
Delivery Status = IF([Actual Delivery]<>"","Received",IF(AND([Expected Delivery]<>"",[Expected Delivery]<TODAY()),"⚠ Overdue","On Track"))

## Job Summary
Job Summary — BOM Post-Release Additions | [6 empty] | Auto-calculated
Job No. | Job Description | BOM Release Date | # Additions | Total Cost Impact | Items Pending | Items Ordered | Items Received | Notes
801253 | Aviation Refueller — Unit A | 2026-07-14
801254 | Aviation Refueller Mk4 | 2026-07-28
801256 | Fuel Tanker — Rear Config | 2026-07-21
801257 | Fuel Tanker — Std Config | 2026-07-21
801258 | Aviation Refueller — Unit B | 2026-07-28
801215
801216
801217
801218
801219
801235
801236
801237
801238
801239
801240
801241
801252
801255
801259
801260
801267
801269
801270
801281

## Reference
Reason Code | Procurement Status | Why was this part added after BOM release?
Engineering Change | Pending | Design was updated after BOM issued
Customer Request | PO Raised | Customer requested additional item
Error / Omission | Ordered | Part missing from original BOM
Design Update | Partial Receipt | Internal design revision
Substitution | Complete | Original part replaced with equivalent
Additional Scope | Cancelled | Scope increased after release
Other |  | Document reason in Notes column

## Monthly Trend
Monthly BOM Additions — Value & Quantity |  |  |  | Auto from BOM Additions
Month | Month Start | # Additions | Total Value (AUD) | Avg Value / Add. | Running Total AUD
Jan-26 | 2026-01-01
Feb-26 | 2026-02-01
Mar-26 | 2026-03-01
Apr-26 | 2026-04-01
May-26 | 2026-05-01
Jun-26 | 2026-06-01
Jul-26 | 2026-07-01
Aug-26 | 2026-08-01
Sep-26 | 2026-09-01
Oct-26 | 2026-10-01
Nov-26 | 2026-11-01
Dec-26 | 2026-12-01
Jan-27 | 2027-01-01
TOTALS